## App Questionnaire - Anthem
v32 Release 03/05/2026 | SharePoint: ElevanceHealth Migration Process Documentation | App Name: | Legacy Provider Finder-Test (Orphan)
MEA190 |  | Information Provided by:
Category | Application Specific Questionnaire | Answer: Yes, No, N/A | Comment | TM Custom Field (To be filled by Kyndryl only) | Kyndryl Comment
Section 1: | High Level Assessment
App specific | Please verify server names and IP addresses that are in scope for this migration event. Note: If P2V is required for any servers in scope, please be advised that the hostname WILL NOT change during migration. If a new hostname is desired, it's recommended that any hostname change occur post-migration at a later date. |  | Please use the "Server Scope" tab within this workbook to document this information. | NA | Confirm the server list and IP information with the app owner and validate this information within Transition Manager. Ensure any secondary NICs/IP addresses are accounted for as they will be needed for Cloudscape, firewall, and other downstream processes.
App specific | Is the application referred to by other names (or acronyms)? |  |  | NA
App specific | Do servers in scope for this migration event reside in the DMZ? |  |  | NA | DMZ: 1. F5 configuration needs to be checked to see if there is a/confirm a VIP 2. Server needs to be checked for external access -> NAT 3. If check not successful, have to request NAT information from FW team, if any 4. If external access, special FW rules for NAT need to be requested to allow traffic from Internet to NAT 5. After application team verifies load balancer, Terry Pack (Elevance Health) team needs to be notified to do security scans prior to activation of NAT and NAT FW rules.
App specific | Do servers in scope for this migration event host Teradata? |  |  | NA | Most Teradata systems will be migrated to AWS. (SOA/Datapower).
App specific | Do servers in scope for this migration event interact with Exadata? If so: 1. Is Exadata hosted on the migration event servers, or do the migration event servers simply establish connections to Exadata? 2. What is the Exadata server host name, IP and VIP (if used)? 3. What are the database name(s) being used? 4. How is the connection established (JDBC, LDAP, etc)? Please share connection string and port information. 5. Are the Exadata database(s) shared by other applications? |  |  | NA | Exadata Considerations Work with the app owner(s) to determine if Exadata DBs need to be migrated as part of the migration event. For DBs that are shared between multiple applications, there must be consensus between the app owners to move forward with the DB migration. Consult with the Exadata team (Jyothy, Gary). Additional coordination will be needed for migration tasks and to determine if a DB version upgrade is required. Please note that If a DB version upgrade is required, ensure app owner is aware.
App specific | Do servers in scope for this migration event share a server with other applications? If so, please specify. |  |  | NA | Verify dependencies in TM.
App specific | Do servers in scope for this migration event connect cross environment (i.e. Dev, QA, UAT, Staging, Prod etc.)? (We are looking for cross-environment dependencies - e.g. networks, endpoints or services). |  |  | NA
App specific | For servers in scope for this migration event, are you aware of any security vulnerabilities that need to be remediated? |  |  | NA | The Elevance Health Security team (Erik Hoffman) will execute vulnerability scans against workloads to be migrated. If vulnerabilities are identified, the app team must remediate or provide an exception. The Elevance Health Security Team requires that TLS 1.2 (or above) be implemented. Transport Layer Security (TLS), is an encryption protocol designed to provide communications security over a computer network. This framework provides privacy between the different endpoints of data transmission and ensures the data’s integrity.
Documentation | Are you able to provide architectural documentation/diagrams of the application environment? |  |  | NA | Before requesting documentation from the app owner, architect should confirm if documentation was previously provided or created by APOC. Steps on how to do this: 1. Verify if the app is listed in the APOC documentation index. https://kyndryl.sharepoint.com/sites/AnthemCirrusTTProgram/Shared%20Documents/Forms/AllItems.aspx?RootFolder=%2Fsites%2FAnthemCirrusTTProgram%2FShared%20Documents%2FTransformation%20work%20streams%2FAPOC&FolderCTID=0x012000E28970F06B1471489CC47C505BB1AAE8 2. If documentation exists, ensure within TM the “APOC Workshop” and “APOC Workshop docs link” fields are updated. 3. Architect reviews APOC documentation prior to AAQ review with the app team. 4. Include APOC team in the AAQ call as needed. (Gerhardt Meldau is our primary contact for APOC).
Downtime | Are there any application team tasks that need to be executed prior to shutting down server(s) for the cutover (e.g. stopping services, bringing down interfaces, etc.)? If so, how much time is required to execute those tasks? |  |  | NA
Testing | Does this application require an external testing team? What is their availability? |  |  | NA
3rd Party Support | Is the application provided by a 3rd party vendor? If so: 1. Is this version of the application under a support agreement? 2. Can vendor support resources be engaged in case of issues during the migration? |  |  | NA
Service Now | Does this application team have a QUEUE name in Service now? Note: The queue name is required to create the cutover change request. The queue name is also mandatory if a LB request is submitted. |  |  | NA | The queue name will be used to assign tasks such as shutdown/startup of applications during the cutover window, as well as the cutover change request and LB requests as required.
Section 2: | Technical Assessment
Network | Do servers in scope for this migration event use a Load Balancer (LB)? If yes: 1. Is it a hardware or software load balancer? (are sub-pools/microservices being used?) 2. What ports need to be opened? 3. What are the VIP(s) and/or DNS name(s) used for this application? 4. Are Akamai services being used? 5. Do external apps point to this VIP/s? 6. Does this application use load balancing across data centers, HA or DRs? If yes, specific the domain names. 7. What is the BarometerIT Number or APM Number related to your application? 8. What is your Email Distribution List? 9. Does your load balancer requires NOSNAT? |  | 1. 2. 3. 4. 5. 6. 7. 8. 9. | Load balancer | If an F5 LB is migrating to we need to coordinate this migration activity at least one week in advance. If the certificate is bound to the F5 by IP, there will be an issue post-migration. Please reference the question on certificates for additional information. These internal Elevance Health tools can be used to lookup F5/VIP Information. If sub-pools are used, our lookup tool might not be able to find the load balancers. Need to gather as much information as possible from the app owner. F5 Configuration Lookup (single IP) https://collaborate.wellpoint.com/sites/F5ENT/customer/SitePages/Configuration%20Lookup.aspx VIP Config Lookup (bulk IP). Recommendation: No more than 5 at a time. https://mostl-che-nms-03.mgmt.internal.das/f5_stuff.html
Network | Does your application use Load Balanced Domain Name (LBDN)?
Network | Do servers in scope for this migration event use hardcoded IP addresses? (e.g.: certificates, handheld devices, configuration files, etc.). The /etc/hosts file is a good example of a configuration file that may contain hardcoded IP addresses. Application owners need to ensure there are not hardcoded IPs and if there are any those need to be remediated with hostnames before the cutover. |  |  | Hardcoded IP address | Please reference the question on certificates for addtitional information. Tableau Considerations The Tableau executable contains a hardcoded IP address. In order to migrate this application, a new build at the target is required.
Security | Do servers in scope for this migration event use certificates? Does a connection to pki.wellpoint.com is required for validating MQ, DB, Middleware,etc? If so, please consider it on the firewall rules. |  | SNOW QUEUE: SECURITY CERTIFICATE MANAGEMENT Certificate contacts matt.daugherty@anthem.com Cristopher R. Ingalls (cristopher.ingalls@anthem.com ) matthew.visnich@anthem.com dl-certificatemanagement@anthem.com dl-sshkeymanagement@anthem.com | NA | Certificates should be bound to hostname/FQDN, not IP address. Please note that Elevance Health owns the management of certificates. Certificate Lookup Tool: https://share.antheminc.com/teams/EE/PublicKnowledgeBase/How%20Do%20I/How%20Do%20I%20Search%20All%20Venafi%20Managed%20Certificates%20By%20SAN.docx?Web=1 Certificate Management Sharepoint Site https://share.antheminc.com/teams/EE/PublicKnowledgeBase/SitePages/Home.aspx and the Team’s DL is DL-CertificateManagement@anthem.com How to Renew a Cert https://share.antheminc.com/teams/EE/PublicKnowledgeBase/_layouts/15/WopiFrame.aspx?sourcedoc=/teams/EE/PublicKnowledgeBase/How%20Do%20I/How%20Do%20I%20Renew%20A%20Certificate.docx&action=default
File Shares & External Storage | Please provide any external storage requirements for servers in scope for this migration event. 1. NAS 2. NFS/CIFS filesystems? |  |  | External Storage NFS or CIFS Filesystem needed | Please provide the name and path information of the NAS server and mount point.
Disaster Recovery | Do servers in scope for this migration event have Disaster Recovery configured? If yes: 1. What are DR hostnames? 2. |  |  | Disaster Recovery | Understand how DR is being done. If the application team does not know, contact the account team.
Operational Resilince | Are there servers in your Application that need to be hosted in two different locations? (High Availability) |  |  | Backup Recovery | The purpose of this question is find out if there are any restore requirements for application backups made in the original/source datacenter.
Middleware | Do servers in scope for this migration event utilize Middleware? If so, please share the following information (1) application URL for web applications -- front-end, back-end (2) application health/validation URLs (3) monitoring -- Dynatrace, iAPI (4) other dependency details - database (Oracle, MySQL, DB2, SQL Server) - message queueing (EMS, MQ) - API endpoints (Mashery, DataPower) - Internet Information Services (IIS) (5) cloud integration (BigQuery, GCS) (6) Enterprise Service Bus (what is the connection information to the host?) |  |  | App uses Middleware | Can be captured in the Runbook and HxH details. Note: Default configuration of IIS is to use Port 80 or 443. However, need to confirm if it's in use. The port can be customized.
Database | Do servers in scope for this migration event use database(s)? If yes, please provide connection details. 1) Type: e.g. DB2-LUW/Oracle/Memsql/MySQL/SQL Server/Postgres 2) Source IP, Target IP, and Target Port. 3) Connection string(s). 4) Current DB Server(s) used 5) Current DB Name(s) 6) Can application be connected back to Elevance Health Data center once application migrates? 7) Is log shipping used? 8) Any additional DB requirements/considerations? |  | Please use the "Firewall" tab within this workbook to document this information. | NA | Make sure we understand if there is any impact on how databases/database VMs run on physical hardware. Should DB instances be grouped together? If log shipping is used, confirm where the logs are being sent and which ports are in use. This will be needed for the firewall request.
Database | Is there a requirement to replicate temporary DB directories to target servers? |  |  | NA | This need to discussed and confirmed with respective DB admins during the application questionnaire discussion. As a general guideline, it's best NOT to migrate temporary DB directories unless the app team requires them for correct function of their application. Verifying this information will ensure there isn't unnecessary overhead for the migration facility and target server(s).
Licenses | Do servers in scope for this migration event have specific licenses to be managed as a result of migrating? (Describe the licensing type this application uses: (e.g. User Based, CPU, Per Instance, Enterprise, Site, IP, Mac, Data Center, Other) |  |  | Specific License | Focus closely on DB and middleware.
HA | Do servers in scope for this migration event use clustering? * Application * Server * Database * GPFS - IBM Spectrum Scale |  |  | Clustered App | For clusters, we need to verify how many nodes and get the cluster IP's (b/c they may not appear in Transition Manager)
HA | Does your application has servers in different locations, what is the reason for that? Should this colocation continue on the target? |  |  |  | The goal for this question is trying to identify servers that are HA / Operational resiliency
App specific | Do you use any Continuous Integration tools or orchestration? Please provide a SME contact or any relevant information. |  |  | NA | Continuous Integration / Orchestration is referring to any tools that the app team may be using to manage their code base. These types of tools are typically used for version management, deployment, promotion, testing, and integration activities across multiple systems and environments. Some of the processes may be automated. Bitbucket & Bamboo are examples of these types of tools. Note: Be advised that migrations involving Bamboo may involve reconfiguration to point to a new Bamboo/UrbanCode node in Ashburn. The Enterprise Tools Group may need to be involved with planning/implementation.
App specific | Do you use any special application-level monitoring for servers in scope for this migration event? If so, please provide any information on how the monitoring is done, what connection(s) from monitoring servers need to be maintained, etc. |  |  | NA
App specific | Do servers in scope for this migration event use or run Containers, Dockers, or Kubernetes? If yes: 1) Please provide a list of the container names and server(s) where they reside. 2) Is the OpenShift Container Platform being used? If yes, CI/CD pipelines will be used to deploy. (Please note that these may need to be built in the new OCP namespaces in Ashburn). The application team will have to establish these new pipelines. If assistance is needed, we should be able to get instructions from the OCP support team. 3) Do these containers need to migrate with the servers in-scope for this event? 4) Are containers run on any of the in-scope servers? If yes, these will be migrated with the server. Note: Additional questions are in the "Kyndryl Comment" column. |  | 1. 2. 3. 4. 5. 6. 7. 8. 9. 10. 11. 12. | NA | 5) How are the containers exposed to the Elevance Health network? * Do they have IPs within the Elevance Health network space (30.x)? * Do they have IPs that are managed by Docker? 6) Do the containers have fully-qualified domain name entries in DNS that require new IPs (10.x)? 7) Are there any special firewall considerations for access to the containers that we might not pick up in our scans? 8) Are there configuration changes on the containers that will need to be done during the cutover? 9) Are there different ways of exposing the images/containers on the network that we need to consider? 10) Are there any orchestration tool that communicates with docker images when they are created. 11) How many docker image does it have? Is there any clustering on the servers, we are migrating, where docker is installed? 12) Are there any IPs configured on docker?
Enterprise File Transfer | Do servers in scope for this migration event use Enterprise File Transfer (EFX)? |  |  | NA | Gather the details on how the EFX exchange is working. This information may already be available in APOC documentation.
Physical Devices | Do servers in scope for this migration event use physical appliance(s)? (e.g. HSM, RSA, SecurID, Tanium, Teradata, etc.) |  |  |  | Does Java need to be installed on the target server? On new targert physical servers it may be required.
User Access | Do you require direct server access after migration? (SSH, RDP, Putty)? From what locations do engineering and/or operations teams connect? |  |  | NA | Collect as much information as possible. Additional analysis to be performed. Can it be virtualized? Can it be migrated (P2V) with our existing tools, or is it proprietary?
User Access | Is there any security service affinity with servers in scope for this migration event (e.g. two-factor external authentication, SiteMinder, Ping Identity, CyberArk). |  |  | NA | SiteMinder Considerations Due to IP address change, there may be a need to re-register the Siteminder service agent post-cutover.
User Access | Do servers in scope for this migration event require a separate client user interface? (Choose any one of the following: Citrix, Fat, Thin or Web Browser) |  |  | NA
SMTP | Do servers in scope for this migration event send emails ? If so, 1.does this include emails to external recipients? 2.does it uses the standard SMTP Relay:smtpinternal.wellpoint.com? If not, which? |  |  | NA | If email is being sent, confirm if standard port 25 is being used. Sometimes a different port is used because of security reasons.
External Interfaces | 1. Do servers in scope for this migration event connect to other services, vendors, or applications outside of the Elevance Health network? Note: This also includes other Cloud providers such as AWS, Google, Azure, etc. 2. Does your environment connect to any other application out of other Data Centers? 3. Any public external IPs used for the application/websites? 4. Are there any external Business to Business Communication (Tunnel) with external Vendors or Banks? 5. Do you connect to any Mainframe resources? Please provide any and all URLs and Ports, Fully Qualified Domain Names (FQDNs), IP Addresses. |  | If Cloud providers are used, be aware that for inbound traffic, App Owners need to provide the source segment from where the traffic can be generated, and for outbound traffic the cloud provider will need to allow the traffic coming from the new IP addresses that will be assigned to the servers being migrated. 1. 2. 3. 4. 5. | NA | Cloud Provider Considerations It's important to understand if IP addresses belonging to 3rd party cloud providers are dynamic or static. If dynamic, we need to capture the range of IP addresses that server could possibly use. This information would be a critical input into the firewall request process. If static, the IP address will be needed as input into the firewall request process. AWS Considerations 1. Is the application using a VPC endpoint? 2. Is the application using a specific URL or IP to access AWS? 3. If the application connects to AWS Snowflake, gather the name of the security group & endpoint, as well as the name of the DBA that supports Snowflake. During cutover, the endpoint security group will have to be updated to include the new source IP. Additionally, the Snowflake DB containing the endpoint routes will need to be updated to whitelist the new source IP. 4. Is there any application requirement that requires a MAC address change. From previous migration event found MAC address change was required within the application to resolve an issue.”
External Interfaces | Is your application used or accessed by EH subsidiaries? (i.e. MBM,Carelon) |  | Help to gather network information, specific FW request or any additional information about subsidiaries. | (i.e. MBM,Carelon)
DNS | Are there any Web URLs used by servers in scope for this migration event? What are the URLs used? |  |  | NA | In cases where web URLs are not load balanced, be advised that they could reference FQDNs that are configured in DNS to route to the original source server IP. Additional DNS updates may be necessary to ensure the URLs resolve to the target server. Note: On the Elevance Health network, the following DNS tool will allow you to specify an IP address and view records that resolve to it. https://dnstools.internal.das/cgi-bin/IP_Research_get.py
Firewall requirements | 1. Can you provide firewall requirements for servers in scope for this migration event? 2. Is authentication or senstive data being passed over ports 20, 21, 23, or 80? 3. Does the application use ICMP (ping) to external sites? 4. Does the application use UDP (e.g. SNA Gateway)? |  | Please be advised that the accuracy of the information provided is crucial to ensure the seamless transition of your application's traffic. Any discrepancies may significantly impact the downtime of your systems during the cutover process. It is imperative that we maintain the highest level of precision in the servers' connectivity, to facilitate a smooth and efficient cutover. | NA | * Focus on capturing information for UDP. Cloudscape does not collect UDP data so that information must come from the app owner. * Traffic over ports 20, 21, 23, and 80 is unencrypted/unsecured. These ports will be allowed if the app owner states they are not performing authentication or transmitting sensitive data through them. * ICMP (ping) requests to hosts outside the Elevance Health network will be evaluated on a case by case basis. Need to put in the firewall request the reason why it's required and the FW team will get it approved if a valid reason exists for having it. * The Elevance Health Firewall Team can take up to two days to implement non-prod firewall requests submitted during the cutover window.
Carbonite | Carbonite Only: Are multiple or recursive mount points used on Windows servers (as in the case with SQL servers)? |  |  | NA | This question only applies to Windows workloads that will be migrated via Carbonite.
AIX | AIX Only: Do servers for this application need to retain the existing MAC address? |  |  | Retain MAC address | This question only applies to AIX workloads. If the app team doesn't know if the MAC address should be retained, please have them confirm with the software vendor.
Test cases | Do servers in scope for this migration event have test cases that can be run? Be sure to discuss the importance of running test cases as outlined in the "Kyndryl Comment" column. |  | Make sure seldom used functions - like end of quarter, maintenance jobs, etc are executed in order to capture those connections by the Discovery Tool (CloudScape) | NA | Test Cases We are asking the application team to fully exercise all aspects of your application and server(s) to assure Cloudscape can monitor all application traffic between each of the servers in scope. This would include application-to-application and application-to-database traffic. If VPN or other external connectivity is used in the environment, that application traffic should be exercised as well. The important point here is to get a complete picture of all of the source, destination, TCP ports and protocols being used by the applications running on these systems. Additionally, if there are UDP requirements, we will need to know those traffic flows separately. Once we have a complete picture of the TCP and UDP application traffic, we will be translating the traffic requirements into firewall policy requests. Please run this comprehensive testing so we can assure comprehensive reports.
App specific | Have you ever involved the SRE team with your application in the past? |  | This will help us determine if the app is likely to need the attention of SRE team during migration |  | If need to engage SRE team please contact Kristi Saeger (kristi.saeger@kyndryl.com) by email and provide the details on the performance concern.
Additional Requirements | Do servers in scope for this migration event have any additional software, hardware, communication, or security requirements not already covered? (e.g. hardware dongles, printers, ports, minimum memory, limited processor or bus speeds, RAID level, CPU, external GPU, storage, networking, USB key, Windows Services; security settings, patch levels, etc.)? |  |  | NA | Part of Pre-migration tasks. Note: For Zerto & Carbonite workloads, MAC addresses are automatically brought over from source to target.

## Server Scope
Hostname | Source IP | Environment | Physical / VM | Operating System | DB | Disaster Recovery
MEA190 | Legacy Provider Finder-Test
vaathmr672 | 30.135.64.125 | Test | AIX-LPAR | AIX | DB2

## Firewall
*Source IP / Subnet Mask (REQUIRED) | *Destination IP / Subnet Mask (REQUIRED) | *Transport Protocol TCP or UDP (REQUIRED) | *Destination Port (REQUIRED) | Type (Inbound or Outbound) | Application Name | Action (Allow/Drop) | Direction of Traffic (*Justify) | Cloudscape/Customer Provided? | Environment | Comments
[6 empty] | Allow | Unidirectional | Customer | Elevance Health
[6 empty] | Allow | Unidirectional | Customer | Elevance Health
[6 empty] | Allow | Unidirectional | Customer | Elevance Health
[6 empty] | Allow | Unidirectional | Customer | Elevance Health
[6 empty] | Allow | Unidirectional | Customer | Elevance Health
[6 empty] | Allow | Unidirectional | Customer | Elevance Health
[6 empty] | Allow | Unidirectional | Customer | Elevance Health
[6 empty] | Allow | Unidirectional | Customer | Elevance Health
[6 empty] | Allow | Unidirectional | Customer | Elevance Health
[6 empty] | Allow | Unidirectional | Customer | Elevance Health
[6 empty] | Allow | Unidirectional | Customer | Elevance Health
[6 empty] | Allow | Unidirectional | Customer | Elevance Health
[6 empty] | Allow | Unidirectional | Customer | Elevance Health
[6 empty] | Allow | Unidirectional | Customer | Elevance Health
[6 empty] | Allow | Unidirectional | Customer | Elevance Health
[6 empty] | Allow | Unidirectional | Customer | Elevance Health
[6 empty] | Allow | Unidirectional | Customer | Elevance Health
[6 empty] | Allow | Unidirectional | Customer | Elevance Health
[6 empty] | Allow | Unidirectional | Customer | Elevance Health
* Please document app owner requested firewall rules here. All fields should be completed. This information is required to generate the firewall request.
* Please note that"Bi-directional" isn't an option in the Anthem environment. Anthem uses stateful firewalls, so return traffic over an established connection is always allowed. For instances in which there are two servers initiating communications with one another, separate uni-directional firewall rules will need to be submitted.

## Field Name in TM
Default/Custom | TM Application fields 4.5.5 | TM Priority(Mandatory/Optional) | Description
Custom | Retain MAC address | Optional | Yes / No
Custom | CICD SME | Optional | Text
Custom | Backup Recovery | Optional | Yes / No
Custom | Backup Required | Optional | Yes / No
Custom | Weekend migration | Optional | Yes / No
Custom | NFS Needed | Optional | Text
Custom | External Storage | Optional | Text
Custom | Specific License | Optional | Text
Custom | Batch tools | Optional | Text
Custom | App uses Middleware | Optional | Text
Custom | Hardcoded IP address | Optional | Text
Custom | Clustered App | Optional | Text
Custom | Load balancer | Optional | Text
Custom | Disaster Recovery | Optional | Yes / No
Custom | Port Requirements | Optional | Text
Custom | URL | Optional | Text
Custom | Box link | Optional | Text

## Cloud A Questionnarie(Optional)
# | Category | Question Status | Application Specific Questionnaire | Response
1 | Application ID | Required | Enter any unique identifier for application.
2 | Application Name | Required | Enter the name of the application. List acronyms or alias in parenthesis.
3 | Application Description | Required | Describe the key functions, capabilities, processes, and data provided by this application.
4 | Application Type | Required | What type of application is this?
5 | Lifecycle strategy | Required | What is the current lifecycle status of the application?
6 | Business Domain | Required | What is the Anthem IT Functional Organization?
7 | Business Processes (Level 2) | Required | What is the Anthm OBA primary function?
8 | Influence Revenue | Required | Does this app influence Anthem Financial Performance?
9 | Functional Complexity Level | Required | Select the appropriate functional complexity of the application.
10 | Degree of Functional Overlap with Other Applications |  | What is the opportunity level for consolidating this application into another Anthem application?
11 | Data Security, Privacy and Regulatory Requirements | Required | Select level of application functionality related to data security and privacy.
12 | Audits by External Agencies | Required | If applicable, which external agency audits this application?
13 | Anthem DR_TIER | Required | What is the Anthem DR Tier level? See attached DR Tier definitions.
14 | Estimated Number of Peak Concurrent Users | Required | What is the estimated number of concurrent users at peak traffic times?
15 | Peak Monthly Usage | Required | What are the peak monthly usage frequency ?
16 | Processing Volume | Required | Select approximate peak online transaction volume.
17 | Data Transfer Requirements |  | Select the most appropriate option related to latency between users / external systems and this application as well as any large data files or high throughput data requirements. See the List of Values tabe for descriptions for each option.
18 | On Premises Requirements | Required | Does the app need to reside on prem for security performance or other technical reasons?
19 | Data Placement Requirements | Required | Are there geographic restrictions for applications or data?
20 | Data Placement / On Premises Requirements Reasons | Optional | Data Placement / On Premises Requirements Reasons
21 | Comments on Significant Nonfunctional Requirements | Optional | Provide any additional nonfunctional requirements we should be aware of.
22 | Interface Technologies and Standards | Required | What are the message and transport technologies and standards (e.g. REST, SOAP, JMS, etc.)?
23 | Application Frameworks and Languages | Required | Application Programming Language / Framework (J2EE, Mainframe Cobol, .NET)
24 | Stateless? | Required | Is this application stateless?
25 | DevOps Maturity Level | Required | Select level of adoption of DevOps automation and practices.
26 | Operating System Full Name | Required | What is the Operating System Full Name (Vendor - Product - Version - Service Pack if known)?
27 | Web Server Software | Required | What Web Server Software does this application use? Leave blank if this is not applicable.
28 | Application & Middleware Software | Required | What Application & Middleware Software does this application use? Leave blank if not applicable.
29 | Database Software | Required | What is the database type and version? Leave blank if not applicable.
30 | Production Server Count | Required | What is the count of production server (physical and virtual servers) associated to this application?
31 | Out of Support Technologies | Optional | Does this application have data with specific any out of support technologies?
32 | Interface Counts | Required | Select approximate number of data interfaces.
33 | Interface Type | Required | What is the type of interface (e.g. synchronous, asynchronous)?
34 | External Interfaces | Required | Does this application have extrenal interfaces?
35 | Average Number of Defects Per Year | Required | How many defects are created per year on average?
36 | Average Number of Enhancements Per Year | Required | How many functional enhancements are requested per year on average?
37 | Number of Production Incidents per Year | Required | How many incidents come up in production per year on average?
38 | Current Issues | Optional | List any known technology issues such as performance or stability.
39 | IT Owner / Contact | Required | Who is the IT Owner/Contact?
40 | Application Startup Time Requirements |  | Is there any application startup time in place?
41 | Application Modernization Comments | Optional | Please add any additional comments or information you believe would help us determine the treatment for this application. You can also clarify your responses to other fields in this column.
42 | Reference Architecture | Optional | Please populate the reference architecture for the applications
Cloud Advisory Anthem questionnaire questions.
This tab should only be used for applications that are in scope for cloud application affinity analysis.

## List of Values
List of Values
Asset Type | Picklist Name | Picklist Label | Comments
YN
Global List | YN | < Please Select >
Global List | YN | Yes
Global List | YN | No
YN
Global List | YN | < Please Select >
Global List | YN | Yes
Global List | YN | No
Global List | YN | Not sure
VHMLNA
Global List | VHMLNA | < Please Select >
Global List | VHMLNA | Very High
Global List | VHMLNA | High
Global List | VHMLNA | Moderate
Global List | VHMLNA | Low
Global List | VHMLNA | Not Applicable
Application Fields
Application Current Lifecycle Status
Application | Application Current Lifecycle Status | < Please Select >
Application | Application Current Lifecycle Status | Active (In Production)- No Major Change Planned | These apps are running the business and will be central to the analysis
Application | Application Current Lifecycle Status | Active (In Production)- Major Change Planned | These apps are running the business and will be central to the analysis
Application | Application Current Lifecycle Status | Conception / Planning / Development Phase | These apps are assumed to consider cloud as they are designed
Application | Application Current Lifecycle Status | Inactive (Already Decommissioned) | These apps have been retired and should not be included in the analysis
Application | Application Current Lifecycle Status | Inactive (Needs to be Decommissioned) | These apps need to be retired
Application | Application Current Lifecycle Status | Managed Service (Hosted by 3rd Party) | These apps are hosted and managed by a 3rd party and not included in the analysis
Application | Application Current Lifecycle Status | Other | If none of the other options apply, select this option and provide comments
Business Processes (Level 2)
Application | Business Processes (Level 2) | < Please Select >
Application | Business Processes (Level 2) | 302 - Finance Management (2020)
Application | Business Processes (Level 2) | 304 - Information Management (2020)
Application | Business Processes (Level 2) | 206 - Member Management (2020)
Application | Business Processes (Level 2) | 210 - Program Integrity Management (2020)
Application | Business Processes (Level 2) | 212 - Sales Management (2020)
Application | Business Processes (Level 2) | 203 - Customer Management (2020)
Application | Business Processes (Level 2) | 202 - Constituent Service Management (2020)
Application | Business Processes (Level 2) | 303 - Human Resource Management (2020)
Application | Business Processes (Level 2) | 205 - Health Management (2020)
Application | Business Processes (Level 2) | 104 - Strategy Management (2020)
Application | Business Processes (Level 2) | 201 - Claim Management (2020)
Application | Business Processes (Level 2) | 103 - Product Management (2020)
Application | Business Processes (Level 2) | 204 - Encounter Management (2020)
Application | Business Processes (Level 2) | 101 - Communication Management (2020)
Application | Business Processes (Level 2) | 211 - Provider Management (2020)
Application | Business Processes (Level 2) | 301 - Execution Management (2020)
Application | Business Processes (Level 2) | 306 - Technology Business Management (2020)
Application | Business Processes (Level 2) | 102 - Marketing Management (2020)
Application | Business Processes (Level 2) | 305 - Legal and Compliance Management (2020)
Application | Business Processes (Level 2) | 209 - Prescription Dispensing Fulfillment Management (2020)
Application | Business Processes (Level 2) | 207 - Network Management (2020)
Application | Business Processes (Level 2) | 208 - Pharmaceutical Drug Purchasing Management (2020)
Application | Business Processes (Level 2) | Other
Influences Revenue
Application | Influences Revenue | < Please Select >
Application | Influences Revenue | Yes - Market/Customer facing that directly impacts revenue and/or profitability
Application | Influences Revenue | Yes - Internal application that directly impact revenue and/or profitability
Application | Influences Revenue | No - No direct impact on revenue and/or profitability
Application | Influences Revenue | Not sure
Functional Complexity Level
Application | Functional Complexity Level | < Please Select >
Application | Functional Complexity Level | Very High - Spans multiple business functions / enterprise level application-
Application | Functional Complexity Level | High - Many business workflows / highly complex business logic
Application | Functional Complexity Level | Moderate - A few business workflows / moderate complexity business logic
Application | Functional Complexity Level | Low - Sub-process level only and/or very simple business logic
Application | Functional Complexity Level | Other
Integration Complexity
Application | Integration Complexity | < Please Select >
Application | Integration Complexity | Extremely complex interfaces
Application | Integration Complexity | >10 interfaces OR non-standard protocols and technologies OR very specific and complex requirements for the interfaces.
Application | Integration Complexity | Between 3 and 10 using all standard interface protocols and technologies
Application | Integration Complexity | Three or less unique interfaces, all standard interface protocols and technologies
Application | Integration Complexity | Standalone, no interfaces
Application | Integration Complexity | Other
Application Type
Application | Application Type | < Please Select >
Application | Application Type | In-house (including modified COTS)
Application | Application Type | Commerical Off-the-Shelf (COTS)
Application | Application Type | Third-party
Application | Application Type | Complex Hybrid
Application | Application Type | SaaS
Business Criticality
Application | Business Criticality | < Please Select >
Application | Business Criticality | Very High - Application availability is more than 90% | System downtime results in business (enterprise) stops OR system is required to be available for regulatory purposes
Application | Business Criticality | High - Application availability is between 80% to 90% | System downtime results in process shut down
Application | Business Criticality | Moderate - Application availability is 60% to 80% | System downtime creates some business disruption or inconvenience but operations continue
Application | Business Criticality | Low - Application availability is less than 60% | System downtime creates inconvenience but workarounds are possible
Application | Business Criticality | Not Critical - Application availability does not matter (not a critical or revenue influencing application) | Not Critical = System downtime does not impact the business.
Dr_Tier Values
Application | Dr_Tier | <Please Select>
Application | Dr_Tier | 0,1,80,81,90,91 | Very High
Application | Dr_Tier | 2,3,82,83,92,93 | High
Application | Dr_Tier | 4,84,94 | Moderate
Application | Dr_Tier | 5,85,95 | Low
Application | Dr_Tier | 6,86,96 | Not Critical
Degree of Functional Overlap with Other Applications
Application | Degree of Functional Overlap | < Please Select >
Application | Degree of Functional Overlap | High - This application overlaps with at least one other application to a large degree | This application overlaps with at least one other application to a large degree
Application | Degree of Functional Overlap | Moderate | This application overlaps with at least one other application to a moderate degree
Application | Degree of Functional Overlap | Low | This application overlaps with at least one other application to a Low degree
Application | Degree of Functional Overlap | None | This application does not overlap in a meaningful way with any other applications
Application | Degree of Functional Overlap | Not Sure | Not sure of the functional overlap
Growth Trend
Application | Growth Trend | < Please Select >
Application | Growth Trend | Steady
Application | Growth Trend | Growing
Application | Growth Trend | Substantially Growing
Application | Growth Trend | Shrinking
Estimated Number of Peak Concurrent Users
Application | Estimated Number of Peak Concurrent Users | < Please Select >
Application | Estimated Number of Peak Concurrent Users | 0-100
Application | Estimated Number of Peak Concurrent Users | 101-500
Application | Estimated Number of Peak Concurrent Users | 501-999
Application | Estimated Number of Peak Concurrent Users | 1,000-5,000
Application | Estimated Number of Peak Concurrent Users | 5,001-9,999
Application | Estimated Number of Peak Concurrent Users | 10,000-100,000
Application | Estimated Number of Peak Concurrent Users | >100,000
Data Transfer Requirements
Application | Data Transfer Requirements | < Please Select > | Note: Data transfer rates: frequency and size of I/O
Application | Data Transfer Requirements | Low - High latency between data and application is acceptable & low data transfer rates relative to compute usage | High latency between data and application is acceptable & low data transfer rates relative to compute usage.
Application | Data Transfer Requirements | Moderate - Moderate latency between data and application is acceptable and moderate data transfer rates | Moderate latency between data and application is acceptable and moderate data transfer rates.
Application | Data Transfer Requirements | High - Low latency between data and application is required - OR - high data transfer rates | Low latency between data and application is required - OR - high data transfer rates.
Application | Data Transfer Requirements | Very High - Low latency between data and application is required - AND - high data transfer rates | Low latency between data and application is required - AND - high data transfer rates.
Availability Requirements
Application | Availability Requirements | < Please Select >
Application | Availability Requirements | Very High - All 4 Weeks
Application | Availability Requirements | High - 3 Weeks
Application | Availability Requirements | Moderate - 2 Weeks
Application | Availability Requirements | Low - 1 Week
Interface Complexity
Application | Interface Complexity | < Please Select >
Application | Interface Complexity | Very High - Application has interfaced with more than 10 applications | Extremely complex interfaces - further discussion is required to determine feasibility
Application | Interface Complexity | High - Application has interfaced with 5 to 10 applications | The number of inbound or outbound interfaces is greater than 10, or there are non-standard protocols and technologies, or there are very specific and complex requirements for the interfaces.
Application | Interface Complexity | Moderate - Application has interfaced with 3 to 4 applications | More than three but less than 10 unique interfaces, all standard interface protocols and technologies
Application | Interface Complexity | Low - Application has interfaced with 1 to 2 applications | Three or less unique interfaces, all standard interface protocols and technologies
Application | Interface Complexity | None - Application has no interfaces | Standalone, no interfaces
Data Security, Privacy and Regulatory Requirements
Application | Data Security, Privacy and Regulatory Requirements | < Please Select >
Application | Data Security, Privacy and Regulatory Requirements | High - Application has extensive features for handling security and regulatory requirements
Application | Data Security, Privacy and Regulatory Requirements | Medium - Application has some technical considerations for secure data storage and transport
Application | Data Security, Privacy and Regulatory Requirements | Low - Minor/No Limitations over data security, privacy and regulatory requirements
Degree of Functional Overlap with Other Applications
Application | Degree of Functional Overlap with Other Applications | < Please Select >
Application | Degree of Functional Overlap with Other Applications | High - Most or all of this application can be consolidated | This application overlaps with at least one other application to a large degree
Application | Degree of Functional Overlap with Other Applications | Medium - About half of this application can be consolidated | This application overlaps with at least one other application to a moderate degree
Application | Degree of Functional Overlap with Other Applications | Low - Some portions of this application can be consolidated | This application overlaps with at least one other application to a Low degree
Application | Degree of Functional Overlap with Other Applications | None -This application cannot be consolidated | This application does not overlap in a meaningful way with any other applications
Application | Degree of Functional Overlap with Other Applications | Not sure | Not sure of the functional overlap
Regulatory Compliance Level
Application | Regulatory Compliance Level | < Please Select >
Application | Regulatory Compliance Level | Very Frequent
Application | Regulatory Compliance Level | Occasionally
Application | Regulatory Compliance Level | Never
Processing Volume
Application | Processing Volume | < Please Select > | Does this application process large volume of data?
Application | Processing Volume | Very High (e.g. 100,000 /hour) | Does this application process large volume of data?
Application | Processing Volume | High (e.g. 10,000 / hour) | Does this application process large volume of data?
Application | Processing Volume | Medium (e.g 1,000 / hour) | Does this application process large volume of data?
Application | Processing Volume | Low (e.g 100 / hour) | Does this application process large volume of data?
Application | Processing Volume | Batch processes only | Does this application process large volume of data?
Interface Counts
Application | Interface Counts | < Please Select >
Application | Interface Counts | > 100
Application | Interface Counts | 51-100
Application | Interface Counts | 21-50
Application | Interface Counts | 11-20
Application | Interface Counts | 0-10
Application | Interface Counts | Standalone
Interface Types
Application | Interface Types | < Please Select >
Application | Interface Types | Synchronous (Very fast response times needed)
Application | Interface Types | Asychronous (Vast response times needed)
Application | Interface Types | Aysnchronous (One way)
Application | Interface Types | Batch only
Application | Interface Types | Multiple interface types
Average Number of Defects Per Year
Application | Average Number of Defects Per Year | < Please Select > | How many defects are created per year on average? If possible, please provide a summary of the % of each type of defects in the comments.
Application | Average Number of Defects Per Year | < Please Select > | How many defects are created per year on average? If possible, please provide a summary of the % of each type of defects in the comments.
Application | Average Number of Defects Per Year | 50-100 | How many defects are created per year on average? If possible, please provide a summary of the % of each type of defects in the comments.
Application | Average Number of Defects Per Year | 10-50 | How many defects are created per year on average? If possible, please provide a summary of the % of each type of defects in the comments.
Application | Average Number of Defects Per Year | 0-10 | How many defects are created per year on average? If possible, please provide a summary of the % of each type of defects in the comments.
Average Number of Enhancements Per Year
Application | Average Number of Enhancements Per Year | < Please Select > | How many functional enhancements are requested per year on average?
Application | Average Number of Enhancements Per Year | >100 | How many functional enhancements are requested per year on average?
Application | Average Number of Enhancements Per Year | 50-100 | How many functional enhancements are requested per year on average?
Application | Average Number of Enhancements Per Year | 10-50 | How many functional enhancements are requested per year on average?
Application | Average Number of Enhancements Per Year | 0-10 | How many functional enhancements are requested per year on average?
Number of Production Incidents per Year
Application | Number of Production Incidents per Year | < Please Select > | How many incidents come up in production per year on average?
Application | Number of Production Incidents per Year | >100 | How many incidents come up in production per year on average?
Application | Number of Production Incidents per Year | 50-100 | How many incidents come up in production per year on average?
Application | Number of Production Incidents per Year | 10-50 | How many incidents come up in production per year on average?
Application | Number of Production Incidents per Year | 0-10 | How many incidents come up in production per year on average?
DevOps Maturity Level
Application | DevOps Maturity | < Please Select >
Application | DevOps Maturity | Very High - Full CI / CD toolchain, environment configuration and application deployment is fully automated | Full CI / CD toolchain, environment configuration and application deployment is fully automated
Application | DevOps Maturity | High - Full CI / CD toolchain, environment configuration and application deployment is mostly automated with some manual steps | Full CI / CD toolchain, environment configuration and application deployment is mostly automated with some manual steps
Application | DevOps Maturity | Moderate - Some CI / CD capabilities | Some CI / CD capabilities
Application | DevOps Maturity | Low - Low degree of automation, environment configuration and application deployment is manual | Low degree of automation, environment configuration and application deployment is manual
Data Placement Requirements
Application | Data Placement Requirements | < Please Select >
Application | Data Placement Requirements | Must be On Premises
Application | Data Placement Requirements | Must be in State or Region
Application | Data Placement Requirements | Must be in Country
Application | Data Placement Requirements | No Restrictions
On Premises Requirements
Application | On Premises Requirements | < Please Select >
Application | On Premises Requirements | Yes | Does the application need to be on Prem ?
Application | On Premises Requirements | No | Does the application need to be on Prem ?
Stateless
Application | On Premises Requirements | < Please Select >
Application | On Premises Requirements | Yes | Is the application stateless? If not, please briefly describe how state is used / persisted in the comments. If no value is provided, the default value of 'No' will be assumed.
Application | On Premises Requirements | No
Application | On Premises Requirements | Not Sure
Significant Nonfunctional Requirements
Application | Significant Nonfunctional Requirements | < Please Select >
Application | Significant Nonfunctional Requirements | Yes | Please list any significant nonfunctional requirements e.g- Does this application require high scalability? e.g 5 users to 10000 users Does the application require a good performance for a high number of concurrent users at atime?
Application | Significant Nonfunctional Requirements | No
Recommended Disposition
Application | Recommended Disposition | < Please Select >
Application | Recommended Disposition | 1. Transform/Modernize/Major enhancements
Application | Recommended Disposition | 2. Continuously Enhancement
Application | Recommended Disposition | 3. Sustain (Keep alive)
Application | Recommended Disposition | 4. Consolidate functions into other application (which one)
Application | Recommended Disposition | 5. Replace with SaaS or COTS
Application | Recommended Disposition | 6. Retire completely
Application | Recommended Disposition | 7. Already retired/decommissioned
Reference Architecture
Application | Reference Architecture | < Please Select >
Application | Reference Architecture | Mainframe/iSeries
Application | Reference Architecture | Client/Server - Web App
Application | Reference Architecture | Client/Server - Other
Application | Reference Architecture | Desktop
Application | Reference Architecture | Agent Based
Application | Reference Architecture | Complex system (Multi-architecture)
Infrastructure Fields
Infrastructure Type
Infrastructure | Infrastructure Type | < Please Select >
Infrastructure | Infrastructure Type | Physical Server
Infrastructure | Infrastructure Type | Physical Server
Infrastructure | Infrastructure Type | Hardware Appliance
Infrastructure | Infrastructure Type | Cloud Service
Infrastructure | Infrastructure Type | Mainframe
Infrastructure | Infrastructure Type | Other
Cloud Workload Type
Infrastructure | Cloud Workload Type | < Please Select >
Infrastructure | Cloud Workload Type | Beanstalk
Infrastructure | Cloud Workload Type | Big Data
Infrastructure | Cloud Workload Type | Containerized
Infrastructure | Cloud Workload Type | Data Warehouse
Infrastructure | Cloud Workload Type | IaaS
Infrastructure | Cloud Workload Type | IoT
Infrastructure | Cloud Workload Type | PaaS
Infrastructure | Cloud Workload Type | Relational Database Service (RDS)
Infrastructure | Cloud Workload Type | Not a Cloud Service
Environment Type
Infrastructure | Environment Type | < Please Select >
Infrastructure | Environment Type | Production
Infrastructure | Environment Type | Staging
Infrastructure | Environment Type | Disaster Recovery
Infrastructure | Environment Type | Test
Infrastructure | Environment Type | Development
Infrastructure Role
Infrastructure | Infrastructure Role | < Please Select >
Infrastructure | Infrastructure Role | Application
Infrastructure | Infrastructure Role | Database
Infrastructure | Infrastructure Role | Function
Infrastructure | Infrastructure Role | Infrastructure
Infrastructure | Infrastructure Role | Web Server
Infrastructure | Infrastructure Role | Security
Infrastructure | Infrastructure Role | Network
Infrastructure | Infrastructure Role | Other
Server Count
Infrastructure | Server Count | < Please Select >
Infrastructure | Server Count | > 80 | Large
Infrastructure | Server Count | 21-80 | Medium
Infrastructure | Server Count | 1-20 | Small
Interface Fields
Interface Direction
Application Interfaces | Interface Direction | < Please Select >
Application Interfaces | Interface Direction | Inbound | The source application receives information from the target application
Application Interfaces | Interface Direction | Outbound | The source application sends information to the target application
Application Interfaces | Interface Direction | Bi-Directional | The source application sends and receives information from the target application
Data Center Fields
Data Center Type
Data Center | Data Center Type | < Please Select >
Data Center | Data Center Type | Company Data Center - Standard | Standard data center owned / leased by the company
Data Center | Data Center Type | Company Data Center - Disaster Recovery | Disaster Recovery data center owned / leased by the company
Data Center | Data Center Type | Colocation Facility | Data center facility managed by a 3rd party colocation provider
Data Center | Data Center Type | Cloud Provider | Cloud Service Provider facility
Data Center | Data Center Type | Managed Services Provider Facility | Data center facility managed by a 3rd party managed services provider
Data Center | Data Center Type | Other | Other (please specify)
External Interfaces
Application | External Interfaces | < Please Select >
Application | External Interfaces | Yes
Application | External Interfaces | No
Application | External Interfaces | Not Sure
Lifecycle strategy
Application | Lifecycle strategy | < Please Select >
Application | Lifecycle strategy | Minor Enhancements Planned
Application | Lifecycle strategy | Major Transformations Planned
Application | Lifecycle strategy | Keep As-Is
Application | Lifecycle strategy | In Concept or Development Phase
Application | Lifecycle strategy | Planned for consolidation into other
Application | Lifecycle strategy | Planned for SaaS/COTS replacement
Application | Lifecycle strategy | Planned for Retiredment
Application | Lifecycle strategy | Managed Service (Hosted by 3rd Party)
Application | Lifecycle strategy | Inactive (Already Decommissioned/ Sunset)
Application | Lifecycle strategy | Other
TCP
UDP
Physical
VM
Tab to be used by Cloud Advisory Anthem focals.